## Slide 1
Administrative Procedures in Survey Implementation and Protocols to Ensure Data Quality
NFHS Team

## Slide 2
Submission of performance security irrespective of the Phase of fieldwork
Signing of MoA
At any stage, after signing the contract of NFHS-5, FAs are strictly prohibited from making any sort of subcontracting of any of the NFHS-5 activities
FAs must sign a separate undertaking with IIPS before receiving the required number of mini laptops, GPS instruments and CAB equipment
Ensuring essential infrastructure at state office
Administrative responsibilities of FA’s

## Slide 3
FAs attached to university, or government agency will be required to provide a letter (prior to release of first installment) from the parent organization certifying that the FA will be allowed to set up a special bank account for NFHS-5
FAs need to have fully functional office in the state where they undertake the fieldwork
State offices of FA need to have all the basic modern communication facilities along with sufficient storage place to store the CAB materials
Recruitment of core team members with essential qualification and their regular and effective use in survey implementation
Contd..

## Slide 4
FAs must sign an agreement for a minimum duration of 11 months or till the completion of the survey with Core Staffs
Agreement should be on non-judicial stamp paper of Rs. 100/-with Core staffs members whose names are mentioned in the Bid document
In case of any change in core team member of FA, prior permission of IIPS is essential
FAs must provide a copy of bio-data, proofs of identity and minimum qualification of all the staff (field and office including field level investigators), recruited at different stages of survey, well in advance to IIPS
Contd..

## Slide 5
Protocols of M & L implementation by FAs
Hiring of adequate number of field staff at various level for M & L as per NFHS protocols including qualification, salary and DA, before M & L ToT
FA must ensure that all payments to field staff should be transferred in their bank account.
Deputing two staff/ coordinators for M & L ToT at IIPS during Jan 29-31, 2019
Organising state level training for M&L during Feb 7-11, 2019
Mapper and Lister must be graduates in any stream.
All the educational documents of the trainees will be verified by IIPS SPO/PO.

## Slide 6
Contd..
Adequate field practice, acquainted with the real field situation
Provision of additional training
FA will be responsible for any official payment to obtain CEB maps from the Census Office
The Data entry operators should be comprehensively trained by M&L coordinators before preparing excel sheets containing M&L data.

## Slide 7
Quality assurance of M & L data
Planning of M&L operation should be in a phased manner, which may ensure quality monitoring by FA as well as IIPS
Team movement plan must be shared with IIPS
The quality checks by M&L coordinator (s) of Field Agency
SPO/PO/ PIs of NFHS-5/ Official from MoHFW will assess the quality of data collected
Excel sheet containing error free listing data must be counter signed by M & L coordinator of FA and IIPS SPO/ PO before sending to NFHS-5 office

## Slide 8
The FAs must translate all Schedules and manuals (Interviewer’s and CAB) into the appropriate local language(s) using the template of Schedules provided to the FA by IIPS
FAs must seek approval of translated instruments from IIPS.
Recruitment of adequate number of field investigators (MI, HI, FI) as per NFHS protocols including qualification, salary and DA, before main survey TOT to be organized by IIPS.
FA must ensure that all payments to field staff should be transferred in their bank account.
FAs must make provision for group insurance to all the field staffs deployed in NFHS-5.
Preparedness for the Main Survey Fieldwork

## Slide 9
FAs must send four seniors staff per group of state/UTs for main (TOT)
One Social Scientist
One Health Coordinator
One IT coordinator
Demographer
The same independent set of core staff will be responsible for conducting state/UTs level training in local language and field monitoring on regular basis, review of field check tables and organization of feedback sessions.
The age of core team members may not exceed 65 years
Contd..

## Slide 10
FAs must organize state/UTs level training for the main survey just after TOT, as per dates mentioned in the time schedule.
Main Survey Training for Field investigators, supervisors and health investigators – four weeks (28 days) with adequate field practice as per NFHS protocol.
FA must pay salary and DA to the trainees, even for the training period.
FAs must train extra field personnel to compensate the drop out or shortage of manpower
FAs must arrange at least 2 training in those states/UTs where the number of districts are 10 or more
Ensure minimum Educational qualification of the field investigators.
Contd..

## Slide 11
The FA must train extra field personnel to ensure that there is sufficient number of field staff to conduct the fieldwork within the stipulated time period of four months.
Health Coordinator of FA will be jointly responsible for training and supervision of the CAB component
Health coordinator of FA will be responsible for coordinating the activities with IIPS with regard to CAB component including supply, storage and inventory management of CAB consumables and equipment
IT coordinator of FA will be responsible for coordinating with the IT team in the Central Office i.e. IIPS, in overall CAPI related works including data transfer and management.
Minimum of four-day visit is essential for state module PSUs
Minimum of three-day visit is required for district module PSUs
Contd..

## Slide 12
FAs will also be responsible for printing the required number of Biomarker Schedules for the main survey
Arrangements should be made by FAs for additional manpower and logistics for safe transfer of the DBS samples from the field to the designated lab
The receipts of all courier/postal charges made for sending the DBS samples must be submitted to IIPS regularly for reimbursement
Contd..

## Slide 13
FAs must plan all fieldwork activities and inform the fieldwork schedule to IIPS along with details of team movement plan at least one week in advance.
Field work should not be started before getting permission from IIPS
IIPS will release the list of selected households only for 5-6 adjoining districts at a time
FA must not change field work plan/team movement without the approval from the IIPS
Contd..

## Slide 14
FAs are strictly advised to refrain from extending any undue favours to any monitoring staff of IIPS or other monitoring staff
Any direct or indirect interference that hinders the monitoring and supervision work can amount to termination of the contract along with suitable penalty
FAs are required to extend full cooperation to the monitoring personnel from the IIPS/MoHFW/Partners or third party appointed for this purpose
FAs must develop and implement a three-tier monitoring and supervision system
Contd..

## Slide 15
Weekly progress reports should be sent to IIPS on every Friday, in a format prescribed by IIPS
FAs must purchase one GSM modem (dongle) per survey team
FAs will also be responsible for payment of internet charges for transferring data files from the supervisor’s CAPI to IIPS and FA on a daily basis
Ensure Proper inventory of Mini- laptops, CAB equipment and consumables.
Ensure minimum wastage of CAB consumables
Contd..

## Slide 16
Materials (bleach, trowel, tongs, 5 litre wide mouth plastic jar, kerosene and matchbox) needed for disposal of bio-hazardous waste will be purchased and managed by FAs
FAs will take responsibility for any violation of safety norms
In case of any loss/damage of instruments, FA will be responsible for meeting the cost
The cost related to transporting CAB components, CAPI and other materials from FAs to IIPS after completion of the survey will be borne by FAs
The instructions received from IIPS/MoHFW must be strictly followed by FAs for the smooth conduct of the survey
Contd..

## Slide 17
FAs will be sent the selected list of households in each PSU of the district (separate excel sheet) prior to uploading in mini laptops by their IT coordinator in consultation with central office.
For smooth uploading of data in CAPI, M/L works should be completed 30 days in advance of main survey
In case of any loss of instruments (laptop & CAB), FA will be responsible for meeting the cost as per the prescribed norms
In case of any damage of instruments (laptop & CAB), FA will be responsible for meeting the cost after accounting for its depreciation value
Contd..

## Slide 18
Cost of travel and stay of the officials from Field agencies for attending additional training (other than TOT) or review meeting at IIPS/MoHFW will be met by the Field Agency
FA needs to provide all necessary information about newly created districts to IIPS, especially in Delhi and Telangana
FAs should provide functional vehicle with adequate space to each survey team in the main survey
There will be penalty clause(s) in the contract for any delay in completing the survey and poor quality of data
Contd..

## Slide 19
FAs will ensure safe disposal of biomedical waste in PSU (cotton, gloves & lancet)
Materials needed for disposal of bio-hazardous waste will be purchased by FAs
In case of violation of protocol IIPS may stop the field work & call that FAs for special meeting along with representative of MoHFW where FA will have to bear the travel and other expenses on their own.
FAs should instruct field teams to transfer of PSU wise data on day to day basis.
Contd..

## Slide 20
FAs should keep data backup till completion of secondary editing.
FAs will provide weekly progress report (in prescribed format) to IIPS.
FA will be required to print 500 copies of district factsheets and distribute to the officials as per the list provided by IIPS.
Contd..

## Slide 21
Phasing the field operations into two parts and division of larger states into two-three parts and survey implementation in a cluster of 5-6 adjoining districts
Intensified hands-on training of the trainer’s (ToT) of 3 weeks duration for the four core team members of FA’s
One ToT is organized for each phase and also by limiting the number of participants in each ToT
All the core team members will be required to attend the full ToT
All the state level trainings are closely monitored by PIs, SPO/PO, ICF Representatives and Officials from MoHFW
Strategies to ensure the quality of data

## Slide 22
FAs are required to conduct more than one trainings, if they are assigned a state having more than 10 districts
Training for any additional staff may be provided on the cost of FA with prior approval from IIPS
Test will be conducted for investigators
CAPI based survey with the provision of Inbuilt algorithm in CAPI program automatically handles skip patterns, filters, eligibility for questionnaires and sections.
The provision of synchronizing data from interviewer’s CAPI to supervisor’s CAPI provides an opportunity for back check of information to improve data quality.
Contd..

## Slide 23
The inbuilt mechanism of partial save provides opportunities to complete interview in multiple sessions and minimizes respondent’s fatigue.
Use of SyncCloud Technology improves the data synchronization from supervisor CAPI to Central Office, which gives access of the real-time data anywhere in the world, and from any device or computer.
Generating Field Check Table and giving feedback on regular basis
FA may be responsible for secondary editing of data before the final submission as per the protocols decided by IIPS
Contd..

## Slide 24
The protocols used for collection of CAB data have been developed as per the International standards which allow comparability with other DHS surveys.
NFHS uses standard, self calibrating equipment having latest technologies to ensure minimum instrumental errors.
The equipment are also standardised periodically to ensure the accuracy of the measurements.
NFHS follows strict protocols of storage, maintenance, distribution and handling of CAB equipment and consumables to ensure minimal instrumental errors.
Contd..

## Slide 25
NFHS has assigned a distinct role to supervisors in terms of planning of fieldwork at local level, checking of all materials, and reporting procedures.
NFHS evaluates the supervisors before their prior appointment by considering their education, experience and performance in the test conducted by IIPS.
IIPS has developed a stringent field monitoring protocols by establishing quality assurance team in the NFHS central office.
Contd..

## Slide 26
Activities to be carried out | Time Schedule
Submission of Performance Security and Signing of MoA and under taking | On or before January 22, 2019
Hiring of Mappers and Listers | Before January 30, 2019
M& L ToT at IIPS for phase I states | January 29-31, 2019
State level trainings for M& L by FAs | February 07-11, 2019
Procuring of CEB maps | By February 20, 2019
M & L fieldwork in Phase-I | February 15- April 14, 2019
Submission of final excel sheet (error free) | April 30,2019
Activity Map of NFHS-5

## Slide 27
Main Survey ToT by IIPS | May 14-June 01, 2019
State level training by FAs | June 05-July 02, 2019
Field work in Phase-I States | July 05- November 15, 2019
Secondary editing of data | August- November, 2019
Tabulation Plan for state fact sheet and report | October, 2019
Developing state weights & generating indicators | December, 2019
Generation of fact sheet for Phase-I State/ UTs and printing of fact sheets | December, 2019- January 2020

## Slide 28
Hiring of Mappers and Listers for Phase II states | September, 2019
M& L ToT at IIPS for phase II states | September/October, 2019
State level trainings for M& L by FAs for Phase II states | October, 2019
Procuring of CEB maps for Phase II states | By October, 2019
M & L fieldwork in Phase-II | October- December, 2019
Submission of final excel sheet (error free) | December, 2019

## Slide 29
Main Survey ToT by IIPS for Phase II | January, 2020
State level training by FAs for Phase II | February, 2020
Field work in Phase-II States | March-July 2020
Secondary editing of data for Phase II | April- August, 2020
Developing state weights & generating indicators for Phase II | September- October, 2020
Generation of fact sheet for Phase-II State/ UTs and printing of fact sheets for Phase II | November-December, 2020

## Slide 30
Training 5-10% extra manpower to cope-up with field requirement for following NFHS-5 protocols
Ensuring payments to field investigators as per NFHS protocols to minimize dropout of trained staffs
Arrange transportation and accommodation to each survey team.
Timely Payment of DA to field staffs
Strategies to maintain timeline of NFHS-5

## Slide 31
Adequate rest to field staffs to avoid untoward incidents during field works
Provision of group insurance for all field staff
Adherence to NFHS protocols to avoid stoppage of survey and minimizing review meeting
FAs should strictly adhere to the timeline of the survey failing which a penalty equivalent to 0.1% (per week) of the total cost would be imposed
Strategies to maintain timeline of NFHS-5

## Slide 32: Thank You